## Sheet1
Phase | Activity | Start Week | End Week | Total Weeks
Phase 1 – Foundation Setup | Automation Expansion | 1 | 4 | 4 | 1 | 1 | 1 | 1
| JIRA Test Management | 1 | 4 | 4 | 1 | 1 | 1 | 1
| Test Case Structuring | 2 | 6 | 5 |  | 1 | 1 | 1 | 1 | 1
| Environment & Data Management | 1 | 6 | 6 | 1 | 1 | 1 | 1 | 1 | 1
| Shift-Left Design | 1 | 6 | 6 | 1 | 1 | 1 | 1 | 1 | 1
Phase 2 – Efficiency Initiatives | Reusable Test Cases | 3 | 7 | 5 |  |  | 1 | 1 | 1 | 1 | 1
| Testing Team Training | 1 | 8 | 8 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Phase 3 – Effectiveness Enhancements | Test Case Quality | 2 | 7 | 6 |  | 1 | 1 | 1 | 1 | 1 | 1
| End-to-End Traceability | 3 | 7 | 5 |  |  | 1 | 1 | 1 | 1 | 1
| Downstream Coverage | 4 | 8 | 5 |  |  |  | 1 | 1 | 1 | 1 | 1
| BAU Control Testing | 4 | 8 | 5 |  |  |  | 1 | 1 | 1 | 1 | 1
Phase 4 – Governance Controls | Testing KPIs Setup | 5 | 9 | 5 |  |  |  |  | 1 | 1 | 1 | 1 | 1
| Effort Estimation | 5 | 9 | 5 |  |  |  |  | 1 | 1 | 1 | 1 | 1
| Peer Review Controls | 5 | 9 | 5 |  |  |  |  | 1 | 1 | 1 | 1 | 1
| JIRA Release Setup | 6 | 10 | 5 | [5 empty] | 1 | 1 | 1 | 1 | 1
| Unified JIRA Structure | 6 | 10 | 5 | [5 empty] | 1 | 1 | 1 | 1 | 1
| UAT Log Standards | 6 | 10 | 5 | [5 empty] | 1 | 1 | 1 | 1 | 1
Phase 5 – Knowledge Sharing | Share Learnings | 6 | 10 | 5 | [5 empty] | 1 | 1 | 1 | 1 | 1
| Targeted Training | 7 | 10 | 4 | [6 empty] | 1 | 1 | 1 | 1
| Best Practices Review | 7 | 10 | 4 | [6 empty] | 1 | 1 | 1 | 1
Phase 6 – Roadmap Evaluation | Implementation Review | 11 | 12 | 2 | [10 empty] | 1 | 1
| KPI Benefit Assessment | 11 | 12 | 2 | [10 empty] | 1 | 1
| Stakeholder Feedback | 11 | 12 | 2 | [10 empty] | 1 | 1
| Lessons & Next Steps | 11 | 12 | 2 | [10 empty] | 1 | 1